LicitaIQ Bid Readiness Assessment

Opportunity: RFP-AIGOV-0726 - Enterprise AI governance operating model

Buyer: Example Financial Group

Model: readiness-v1.0

Result: Insufficient Evidence

Weighted score: 49.55/100

Confidence: 93%

Immutable O-5 decision: hold

Export approval: approved by Mariana Torres

Approval rationale: Approve the internal review pack as a transparent record of blockers and evidence gaps; this is not bid approval.

External AI invoked: no

Customer document processed: no

Automatic submission: prohibited

Compliance matrix:

1. [insufficient_evidence] Deliver an enterprise AI governance operating model. | Position: Evidence gap | Evidence: ev_ai_architect_profile | Missing: approved_cap_governed_ai, approved_enterprise_ai_governance_reference

2. [met] Facilitate four executive workshops. | Position: Comply subject to team confirmation | Evidence: ev_ai_architect_profile | Missing: none

3. [insufficient_evidence] Confirm delivery-team capacity for the engagement window. | Position: Evidence gap | Evidence: ev_ai_architect_profile | Missing: current_ai_delivery_team_capacity

4. [insufficient_evidence] Establish a commercially supportable response. | Position: Buyer clarification required | Evidence: none | Missing: buyer_budget_range

Deadline and task plan:

- [blocked] Approve governed AI capability | Due: 2026-07-26T17:00:00-06:00 | Hard deadline: no

- [blocked] Confirm workshop delivery team | Due: 2026-07-27T17:00:00-06:00 | Hard deadline: no

- [in_progress] Resolve commercial assumptions | Due: 2026-07-27T17:00:00-06:00 | Hard deadline: no

- [not_started] Buyer submission deadline | Due: 2026-07-29T17:00:00-06:00 | Hard deadline: yes

Executive explanation:

Insufficient Evidence under readiness-v1.0. The explicit weighted score is 49.55/100 and confidence is 93%. The immutable O-5 human decision input is hold. No mandatory compliance failure is hidden. No hard deadline miss is hidden. 2 mandatory evidence gap(s) override score-based readiness. This assessment does not change the human Go/No-Go decision and is not a probability of award.