## Readiness
LicitaIQ Bid Readiness Assessment | RFP-AIGOV-0726 | Enterprise AI governance operating model
Result | Insufficient Evidence | 49.55/100 | 93% confidence
Immutable O-5 decision | hold | Export approval | approved | Mariana Torres
COMPLIANCE MATRIX
# | Mandatory | Status | Requirement | Response position | Evidence | Missing evidence | Due
1 | Yes | insufficient_evidence | Deliver an enterprise AI governance operating model. | Evidence gap | ev_ai_architect_profile | approved_cap_governed_ai, approved_enterprise_ai_governance_reference
2 | Yes | met | Facilitate four executive workshops. | Comply subject to team confirmation | ev_ai_architect_profile
3 | Yes | insufficient_evidence | Confirm delivery-team capacity for the engagement window. | Evidence gap | ev_ai_architect_profile | current_ai_delivery_team_capacity
4 | No | insufficient_evidence | Establish a commercially supportable response. | Buyer clarification required |  | buyer_budget_range
DEADLINE AND TASK PLAN
Task | Owner role | Due | Hard deadline | Status | Dependencies
Approve governed AI capability | owner | 2026-07-26T17:00:00-06:00 | No | blocked
Confirm workshop delivery team | contributor | 2026-07-27T17:00:00-06:00 | No | blocked | task_opp_ai_governance_rfp_01
Resolve commercial assumptions | admin | 2026-07-27T17:00:00-06:00 | No | in_progress
Buyer submission deadline | owner | 2026-07-29T17:00:00-06:00 | Yes | not_started | task_opp_ai_governance_rfp_01, task_opp_ai_governance_rfp_02, task_opp_ai_governance_rfp_03