## Readiness
LicitaIQ Bid Readiness Assessment | EDSA-CLOUD-2026-014 | Managed cloud services framework 2026
Result | Ready with Conditions | 86.05/100 | 93% confidence
Immutable O-5 decision | go | Export approval | approved | Mariana Torres
COMPLIANCE MATRIX
# | Mandatory | Status | Requirement | Response position | Evidence | Missing evidence | Due
1 | Yes | met | Maintain a current ISO/IEC 27001 certification. | Comply | ev_iso_27001_scope
2 | Yes | met | Accept a thirty-six-month framework term. | Comply subject to approved commercial assumptions
3 | Yes | partial | Commit to the authoritative monthly availability threshold. | Clarification required | ev_cloud_migration_reference |  | 2026-07-28T18:00:00-06:00
4 | Yes | met | Submit clarification questions before 27 July 2026 at 18:00. | Planned |  |  | 2026-07-27T18:00:00-06:00
5 | No | met | Support cloud operations, security and FinOps delivery claims. | Comply | ev_iso_27001_scope, ev_cloud_migration_reference
DEADLINE AND TASK PLAN
Task | Owner role | Due | Hard deadline | Status | Dependencies
Submit SLA clarification question | contributor | 2026-07-27T18:00:00-06:00 | Yes | in_progress
Resolve authoritative availability threshold | contributor | 2026-07-30T17:00:00-06:00 | No | blocked | task_opp_cloud_framework_2026_01
Complete commercial and legal review | admin | 2026-08-05T17:00:00-06:00 | No | in_progress
Approve controlled export pack | owner | 2026-08-11T17:00:00-06:00 | No | not_started | task_opp_cloud_framework_2026_02, task_opp_cloud_framework_2026_03
Buyer submission deadline | owner | 2026-08-14T18:00:00-06:00 | Yes | not_started | task_opp_cloud_framework_2026_04